## Cover
SITE BOOK
City of Vancouver — single-family & duplex new-home inspections
Field book aligned with the City’s “When to Request an Inspection” guide for single-detached houses and duplexes. Tick items here or in the companion app, then bring a printed copy to site.
PROJECT
Address
Legal description
Building type | Single-family
Owner
Contractor
Superintendent
Structural engineer
Geotechnical
Energy advisor
Start date
Target occupancy
Notes
PROGRESS
Checklist items closed | 0 of 198
Open deficiencies | 0
Stages passed | 0 of 21
PHASES
Phase | Stages | Summary | Items closed | %
Site & demolition | 1, 2, 3 | Tree protection, safety plan, deconstruction, and temporary power before any excavation. | 0 / 25 | 0%
Foundation & below grade | 4, 5, 6, 7, 8, 9, 10, 11 | Footings through underslab services. Nothing gets buried or poured until it is signed off. | 0 / 54 | 0%
Rough-in, structure & envelope | 12, 13, 14, 15, 16, 17, 18 | Trades in the walls, sheathing, framing, rainscreen, then insulation — in that order. | 0 / 66 | 0%
Finals | 19, 20, 21 | Trade finals first, then electrical, then building. Occupancy follows a passed final building inspection. | 0 / 53 | 0%
DON'T FORGET
Open the Don't forget tab (second sheet). Write the things you personally always miss — extra photos before cover-up, a second permit copy, neighbour notice, lock-off key. Blank rows are ready. This is not the City list.
HOW TO USE THIS WORKBOOK
Don't forget — your personal list. Not City items. Write anything you tend to miss; attach it to a stage or to every inspection.
Stage tracker — book, inspect, and record pass/fail for each of the 21 City stages.
Checklist — every official field item. Status is a dropdown: Open, Done, Deficiency, N/A.
Documents / Permits — letters of assurance, energy reports, and trade permits that must be on site.
Deficiencies — punch list from failed items; close them before you rebook.
Booking guide — 3-1-1 cutoff, reinspection fee triggers, and same-day trade coordination.
DISCLAIMER
This is a field aid compiled from the City of Vancouver guide “When to Request an Inspection” (single-detached house / duplex) and the public inspections pages. It is not legal advice and does not replace the Vancouver Building By-law, approved drawings, professional field reviews, or the inspector’s determination. Confirm current requirements at vancouver.ca before you book. Occupancy permits are not required for houses and laneway houses; permission to occupy follows a passed final building inspection.

## Don't forget
DON'T FORGET |  |  |  |  | Stage list
Personal reminders — not City of Vancouver inspection items. Write the things you tend to miss. Attach each one to a stage or to every inspection. |  |  |  |  | Every inspection
01 · CSP & trees
# | Reminder (write what you always forget) | Attach to | Status | Notes | 02 · Demolition
1 |  | Every inspection |  |  | 03 · Temp power
2 |  | Every inspection |  |  | 04 · Footings
3 |  | Every inspection |  |  | 05 · Drain tile
4 |  | Every inspection |  |  | 06 · Sump & services
5 |  | Every inspection |  |  | 07 · NEC / survey
6 |  | Every inspection |  |  | 08 · U/G electrical
7 |  | Every inspection |  |  | 09 · U/G plumbing
8 |  | Every inspection |  |  | 10 · Underslab
9 |  | Every inspection |  |  | 11 · Hydronic
10 |  | Every inspection |  |  | 12 · Trade rough-ins
11 |  | Every inspection |  |  | 13 · Elec. rough-wire
12 |  | Every inspection |  |  | 14 · Stairs / walls
13 |  | Every inspection |  |  | 15 · Sheathing
14 |  | Every inspection |  |  | 16 · Framing
15 |  | Every inspection |  |  | 17 · Rainscreen
16 |  | Every inspection |  |  | 18 · Insulation / VB
17 |  | Every inspection |  |  | 19 · Trade finals
18 |  | Every inspection |  |  | 20 · Elec. final
19 |  | Every inspection |  |  | 21 · Building final
20 |  | Every inspection
STARTER IDEAS — copy any of these up into a blank row, or ignore them
| City-stamped drawings in the job box — not just a phone or iPad | Every inspection |  | Copy up if this is one you miss
| Extra printed permit copy for the inspector | Every inspection |  | Copy up if this is one you miss
| Site is locked / gate combination current | Every inspection |  | Copy up if this is one you miss
| Photograph tree barriers before demo starts | 01 · CSP & trees |  | Copy up if this is one you miss
| Neighbour notice before noisy take-down | 02 · Demolition |  | Copy up if this is one you miss
| Photograph forms and rebar before the pour | 04 · Footings |  | Copy up if this is one you miss
| Photograph the open trench before backfill | 05 · Drain tile |  | Copy up if this is one you miss
| Warning tape in the trench before cover | 08 · U/G electrical |  | Copy up if this is one you miss
| Confirm plumbing, mechanical, sprinkler, and gas booked the same day | 12 · Trade rough-ins |  | Copy up if this is one you miss
| House wrap on before the framing inspector arrives | 16 · Framing |  | Copy up if this is one you miss
| Energy advisor mid-construction check booked — no drywall until it passes | 18 · Insulation / VB |  | Copy up if this is one you miss
| Address numbers on the house; lock-off / suite key on site | 21 · Building final |  | Copy up if this is one you miss

## Stage tracker
# | Phase | Inspection | When to request | Trades | Same-day coordinate? | Booked | Inspected | Result | Inspector | Items closed | Deficiencies | Notes
1 | Site & demolition | Pre-demolition, tree barrier & construction safety plan | Required prior to demolition. Book against the project address. | Safety, Landscape, Building | [5 empty] | 0 / 5 | 0
2 | Site & demolition | Demolition / deconstruction | Notify the City (3-1-1) before 2 pm one business day prior. | Building, Safety | [5 empty] | 0 / 5 | 0
3 | Site & demolition | Temporary construction service | After demolition, before the temporary service is used. | Electrical | [5 empty] | 0 / 15 | 0
4 | Foundation & below grade | Footings and forms | After formwork is complete, before any concrete is poured. | Building | [5 empty] | 0 / 10 | 0
5 | Foundation & below grade | Drain tile, damp proofing & rainwater leaders | After footings/forms, before backfill. | Plumbing, Building | [5 empty] | 0 / 9 | 0
6 | Foundation & below grade | Sump, sewer & water service | Sanitary/storm to property line must pass before site services are engaged. | Sewer / water, Plumbing | [5 empty] | 0 / 11 | 0
7 | Foundation & below grade | Non-encroachment certificate & field plan review | Before framing. Confirm the foundation sits on the approved plan. | Building | [5 empty] | 0 / 4 | 0
8 | Foundation & below grade | Underground electrical | After footings/forms, before backfill. | Electrical | [5 empty] | 0 / 5 | 0
9 | Foundation & below grade | Below-slab plumbing (inside building) | After footings/forms, before the slab is poured. | Plumbing | [5 empty] | 0 / 7 | 0
10 | Foundation & below grade | Underslab, damp proofing & insulation | After sub-base, vapour barrier, and insulation are in — before the slab pour. | Building | [5 empty] | 0 / 4 | 0
11 | Foundation & below grade | In-slab hydronic heating | Before the slab is poured. Skip and mark N/A if the house has no in-slab heat. | Mechanical, Plumbing | [5 empty] | 0 / 4 | 0
12 | Rough-in, structure & envelope | Plumbing, mechanical, sprinkler & gas rough-in (above ground) | After initial framing, before sheathing. Coordinate all trades on the same day. | Plumbing, Mechanical, Sprinkler, Gas | Book plumbing, mechanical, sprinkler, and gas together. Uncoordinated requests can trigger a re-inspection fee. |  |  |  |  | 0 / 15 | 0
13 | Rough-in, structure & envelope | Electrical service & rough-wire | After underground electrical, before insulation and vapour barrier. | Electrical | Consolidate main, low-voltage, and garage on the same day. |  |  |  |  | 0 / 14 | 0
14 | Rough-in, structure & envelope | Concrete stairs & retaining-wall forms | Before pouring stairs or retaining walls. Mark N/A if none on the project. | Building | [5 empty] | 0 / 5 | 0
15 | Rough-in, structure & envelope | Sheathing | After sheathing, flashings, roofing, deck membranes, doors and windows — before papering the exterior. | Building | [5 empty] | 0 / 11 | 0
16 | Rough-in, structure & envelope | Framing | Before insulation; after sheathing membrane (building paper / house wrap) and all trade rough-ins are complete. | Building | [5 empty] | 0 / 10 | 0
17 | Rough-in, structure & envelope | Rainscreen | After sheathing is accepted, before the scratch coat. Ideally the same day as framing. | Building | [5 empty] | 0 / 4 | 0
18 | Rough-in, structure & envelope | Insulation & vapour barrier | After framing has passed and insulation plus vapour barrier are fully installed. No interior finishes until this is accepted. | Building | [5 empty] | 0 / 7 | 0
19 | Finals | Final plumbing, mechanical, drain tile, sprinkler & gas | After rough-ins, with all fixtures, equipment, appliances, and sprinklers installed and tested — before final building. | Plumbing, Mechanical, Sprinkler, Gas, Sewer / water | Consolidate plumbing, mechanical, sprinkler, drain tile, and gas on the same day. Only the gas permit holder books the gas final. |  |  |  |  | 0 / 18 | 0
20 | Finals | Final electrical | After framing, before final building. Consolidate main, low-voltage, and garage the same day. | Electrical | The builder coordinates main electrical and low-voltage permits. Uncoordinated requests may incur a fee. |  |  |  |  | 0 / 17 | 0
21 | Finals | Final building | After every sub-trade permit is completed. Interior and exterior VBBL items finished. | Building | [5 empty] | 0 / 18 | 0

## Checklist
Stage # | Phase | Inspection | Category | Checklist item | Applies | Status | Deficiency / notes
1 | Site & demolition | CSP & trees | Safety | Construction Safety Plan posted and visible on site (VBBL 8.1.3) | Always
1 | Site & demolition | CSP & trees | Safety | Emergency contact posted on the CSP | Always
1 | Site & demolition | CSP & trees | Trees | Tree protection barriers installed per engineering specifications | Always
1 | Site & demolition | CSP & trees | Site | Site accessible and safe for the inspector | Always
1 | Site & demolition | CSP & trees | Documents | Approved drawings and permit available on site | Always
2 | Site & demolition | Demolition | Hazmat | Hazardous materials removal documentation on site | Always
2 | Site & demolition | Demolition | Site | Demolition and traffic management plans being followed | Always
2 | Site & demolition | Demolition | Trees | Tree barriers maintained during take-down | Always
2 | Site & demolition | Demolition | Site | Dust control in place | Always
2 | Site & demolition | Demolition | Safety | Emergency contact still posted on the CSP (VBBL 8.1.3) | Always
3 | Site & demolition | Temp power | Service | Temp pole located within 3.3 m (10 ft) of the property line | Always
3 | Site & demolition | Temp power | Grounding | Electrode plate or rods installed; plate buried min. 0.6 m (2 ft) | Always
3 | Site & demolition | Temp power | Service | Three braces on the pole | Always
3 | Site & demolition | Temp power | Equipment | CSA-approved equipment only | Always
3 | Site & demolition | Temp power | Clearances | Overhead clearances maintained across roads, lanes, and sidewalks | Always
3 | Site & demolition | Temp power | Service | Overhead conductors supported | Always
3 | Site & demolition | Temp power | Service | Overcurrent protection installed | Always
3 | Site & demolition | Temp power | Meter | Meter height 1.5–1.8 m (5–5.5 ft) per BC Hydro | Always
3 | Site & demolition | Temp power | Meter | Meter in an accessible location | Always
3 | Site & demolition | Temp power | Conductors | White or grey identified conductor | Always
3 | Site & demolition | Temp power | Service | 75 cm (30 in) drip loop | Always
3 | Site & demolition | Temp power | Conductors | UV-resistant conductors | Always
3 | Site & demolition | Temp power | Service | Attachment 15–30 cm (6–12 in) below weather head | Always
3 | Site & demolition | Temp power | Equipment | Weatherproof lockable enclosure | Always
3 | Site & demolition | Temp power | Receptacles | GFCI receptacles with covers where required | Always
4 | Foundation & below grade | Footings | Excavation | Excavation meets WorkSafeBC or a P.Eng. letter is on site | Always
4 | Foundation & below grade | Footings | Safety | Fencing in place if required (VBBL Division B Part 8) | Always
4 | Foundation & below grade | Footings | Excavation | Poly cover in place if required | Always
4 | Foundation & below grade | Footings | Site | Dewatering filter/screen on the catch basin | Always
4 | Foundation & below grade | Footings | Footings | Location and configuration match approved plans | Always
4 | Foundation & below grade | Footings | Footings | Minimum 45 cm (18 in) frost protection, including sunken patios | Always
4 | Foundation & below grade | Footings | Forms | Form depth and width match approved plans | Always
4 | Foundation & below grade | Footings | Forms | Wall height will facilitate finished grades and stairs | Always
4 | Foundation & below grade | Footings | Forms | Reinforcing steel placed as specified before the pour | Always
4 | Foundation & below grade | Footings | Hold | Concrete has not been poured | Always
5 | Foundation & below grade | Drain tile | Site | Old utilities shut off | Always
5 | Foundation & below grade | Drain tile | Drainage | Piping separated to sumps as required | Always
5 | Foundation & below grade | Drain tile | Drain tile | Perforated PVC with weep holes down and lettering up | Always
5 | Foundation & below grade | Drain tile | Drain tile | Minimum 15 cm (6 in) crushed-stone cover (max 10% passing 4 mm sieve) | Always
5 | Foundation & below grade | Drain tile | Drain tile | Correct location and slope to floor/footings | Always
5 | Foundation & below grade | Drain tile | Foundation | Damp proofing complete; honeycombing parged | Always
5 | Foundation & below grade | Drain tile | Rainwater | Solid PVC sewer-grade rainwater leaders, glued and sloped | Always
5 | Foundation & below grade | Drain tile | Rainwater | Leaders supported with hangers or strapping | Always
5 | Foundation & below grade | Drain tile | Hold | Trench remains open — nothing backfilled | Always
6 | Foundation & below grade | Sump & services | Gravity storm | Backwater valve with 90° elbow on gravity storm sump | Always
6 | Foundation & below grade | Sump & services | Gravity storm | Minimum 20.3 cm (8 in) trap; grouted/sealed watertight; min. 43 cm (17 in) depth | Always
6 | Foundation & below grade | Sump & services | Gravity storm | Gravity flow at or above the restriction | Always
6 | Foundation & below grade | Sump & services | Pumped storm | Union, check, and gate valves on pumped storm sump | If applicable
6 | Foundation & below grade | Sump & services | Pumped storm | Pump discharge in the correct flow direction, below restriction | If applicable
6 | Foundation & below grade | Sump & services | Sewer | Min. 6.4 mm (¼ in) pipe grade — 3.2 mm (⅛ in) per foot slope | Always
6 | Foundation & below grade | Sump & services | Sewer | Firm soil or geotechnical remediation; proper bedding before backfill | Always
6 | Foundation & below grade | Sump & services | Backflow | Accessible backwater valve on gravity portions at/above restriction | Always
6 | Foundation & below grade | Sump & services | Water | Water service min. 3.9 cm (1½ in) per NFPA 13D | Always
6 | Foundation & below grade | Sump & services | Water | Pipe type per approvals; 60.9 cm (2 ft) bury; joints leak-tight | Always
6 | Foundation & below grade | Sump & services | Water | Location relative to other services is correct | Always
7 | Foundation & below grade | NEC / survey | Survey | Non-Encroachment Certificate on site | Always
7 | Foundation & below grade | NEC / survey | Location | Foundation location matches approved plans | Always
7 | Foundation & below grade | NEC / survey | Documents | Approved plans on site for field review | Always
7 | Foundation & below grade | NEC / survey | Zoning | Setbacks, height datum, and building envelope still match the permit | Always
8 | Foundation & below grade | U/G electrical | Trench | Trench remains open | Always
8 | Foundation & below grade | U/G electrical | Trench | Conduit or cable on sand or screened soil — not gravel | Always
8 | Foundation & below grade | U/G electrical | Trench | Warning tape 0.3 m (1 ft) below finished grade | Always
8 | Foundation & below grade | U/G electrical | Trench | Sand backfill around conductors | Always
8 | Foundation & below grade | U/G electrical | Under slab | No gravel around basement-slab cable; sand bedding; tape under slab | Always
9 | Foundation & below grade | U/G plumbing | Bedding | Piping on undisturbed soil, free of debris | Always
9 | Foundation & below grade | U/G plumbing | Materials | Approved pipe, bedding, and fittings | Always
9 | Foundation & below grade | U/G plumbing | DWV | Minimum 6.4 mm (¼ in) per foot grade | Always
9 | Foundation & below grade | U/G plumbing | DWV | Piping below slab as designed | Always
9 | Foundation & below grade | U/G plumbing | DWV | DWV under test; joints glued | Always
9 | Foundation & below grade | U/G plumbing | Backflow | Backwater valve if any fixture is below the street | Always
9 | Foundation & below grade | U/G plumbing | Water | Water service installed | Always
10 | Foundation & below grade | Underslab | Moisture | Poly sealed at the perimeter as a moisture barrier | Always
10 | Foundation & below grade | Underslab | Insulation | Minimum R-12 or plan-value rigid under slab and between slab and walls | Always
10 | Foundation & below grade | Underslab | Sub-base | Sub-base prepared; no standing water or organic material | Always
10 | Foundation & below grade | Underslab | Documents | P.Eng. compaction / slab-reinforcement letter where required | Always
11 | Foundation & below grade | Hydronic | Documents | System design and heat-loss summary on site | If applicable
11 | Foundation & below grade | Hydronic | Piping | Piping installed per design | If applicable
11 | Foundation & below grade | Hydronic | Piping | Loop layout matches the design drawings | If applicable
11 | Foundation & below grade | Hydronic | Piping | Loops under pressure test before the pour | If applicable
12 | Rough-in, structure & envelope | Trade rough-ins | Water | Water service size and type per plans and sprinkler design; CSA fittings; watertight joints | Always
12 | Rough-in, structure & envelope | Trade rough-ins | Hydronic | Above-slab hydronic piping and layout per design; mains to mechanical room | If applicable
12 | Rough-in, structure & envelope | Trade rough-ins | Mechanical | Heat-pump placement and line sets per mechanical permit | Always
12 | Rough-in, structure & envelope | Trade rough-ins | Sprinkler | Sprinkler piping insulated / frost-protected where required | Always
12 | Rough-in, structure & envelope | Trade rough-ins | Sprinkler | P.Eng. sealed drawings on site; piping, fittings, and heads per NFPA 13D | Always
12 | Rough-in, structure & envelope | Trade rough-ins | Sprinkler | Backflow protection, clearances, support, and pressure test complete | Always
12 | Rough-in, structure & envelope | Trade rough-ins | DWV | DWV per VBBL Part 7; fixtures, sizes, and loads match plans | Always
12 | Rough-in, structure & envelope | Trade rough-ins | DWV | 6.4 mm (¼ in)/ft grade; under test; supports and expansion joints per Part 7 | Always
12 | Rough-in, structure & envelope | Trade rough-ins | DWV | Pumped drainage only as per sewer permit; backflow only on susceptible portions | Always
12 | Rough-in, structure & envelope | Trade rough-ins | Gas | Approved materials (steel, copper, CSST, or plastic as permitted) | If applicable
12 | Rough-in, structure & envelope | Trade rough-ins | Gas | Sizing per load; CSA B149.1 and Gas Act | If applicable
12 | Rough-in, structure & envelope | Trade rough-ins | Gas | Underground gas 38.1 cm (15 in) bury and air-tested | If applicable
12 | Rough-in, structure & envelope | Trade rough-ins | Gas | Vent connector, sizing, clearances, labelled appliances, regulator location | If applicable
12 | Rough-in, structure & envelope | Trade rough-ins | Wet areas | Tub/shower liners: membrane min. 15.2 cm (6 in) above rim; standing water test to rim | Always
12 | Rough-in, structure & envelope | Trade rough-ins | Water | Accessible shut-offs; CSA fixtures | Always
13 | Rough-in, structure & envelope | Elec. rough-wire | Permit | Work matches the electrical permit description | Always
13 | Rough-in, structure & envelope | Elec. rough-wire | Rough-wire | Protection and vapour-barrier provisions at boxes | Always
13 | Rough-in, structure & envelope | Elec. rough-wire | Circuits | Circuit loading within maximums; dedicated heating circuits | Always
13 | Rough-in, structure & envelope | Elec. rough-wire | Rough-wire | Outlet-box layout complete; box-fill within limits | Always
13 | Rough-in, structure & envelope | Elec. rough-wire | Lighting | Recessed fixtures are IC-rated or have 13 mm clearance | Always
13 | Rough-in, structure & envelope | Elec. rough-wire | Rough-wire | Wiring supported and stapled | Always
13 | Rough-in, structure & envelope | Elec. rough-wire | Clearances | Clearances from pools, bathtubs, hot water, ducts, and B-venting | Always
13 | Rough-in, structure & envelope | Elec. rough-wire | Bonding | Bonding for metal boxes, gas, communications, and piping over 3 m (10 ft) | Always
13 | Rough-in, structure & envelope | Elec. rough-wire | Equipment | CSA equipment throughout | Always
13 | Rough-in, structure & envelope | Elec. rough-wire | Garage | Garage EV-charger ready | Always
13 | Rough-in, structure & envelope | Elec. rough-wire | Service | Copper #6 AWG grounding | Always
13 | Rough-in, structure & envelope | Elec. rough-wire | Service | Service per City of Vancouver / BC Hydro; meter height and location to standard | Always
13 | Rough-in, structure & envelope | Elec. rough-wire | Service | Amperage rating, conductor size/type, load calculation, and disconnect correct | Always
13 | Rough-in, structure & envelope | Elec. rough-wire | Service | Mast height, guy, wires, and kit complete; rain-tight fittings; lockable; CSA | Always
14 | Rough-in, structure & envelope | Stairs / walls | Forms | Forms and rebar installed for grade change over 1.2 m (4 ft) | If applicable
14 | Rough-in, structure & envelope | Stairs / walls | Footings | Frost protection to specified depth (typically 45 cm / 18 in below grade) | If applicable
14 | Rough-in, structure & envelope | Stairs / walls | City property | Any encroachment on City property has an Engineering covenant | If applicable
14 | Rough-in, structure & envelope | Stairs / walls | Documents | P.Eng. field memo on site | If applicable
14 | Rough-in, structure & envelope | Stairs / walls | Survey | Pin survey for boundary walls | If applicable
15 | Rough-in, structure & envelope | Sheathing | Sheathing | Sheathing has appropriate spacing; joints staggered | Always
15 | Rough-in, structure & envelope | Sheathing | Sheathing | Nailing patterns conform to approved / engineer drawings | Always
15 | Rough-in, structure & envelope | Sheathing | Penetrations | Mechanical and electrical wall penetrations sealed per approved details | Always
15 | Rough-in, structure & envelope | Sheathing | Windows | Window mock-up complete (trim, flashings, end dams) matching approved plans | Always
15 | Rough-in, structure & envelope | Sheathing | Windows | Door, window, and skylight size and location match plans (VBBL 9.7) | Always
15 | Rough-in, structure & envelope | Sheathing | Windows | Window type (material and configuration) matches approved plans | Always
15 | Rough-in, structure & envelope | Sheathing | Mechanical | Deck ventilation over living space completed | Always
15 | Rough-in, structure & envelope | Sheathing | Mechanical | HRV location meets serviceability requirements | Always
15 | Rough-in, structure & envelope | Sheathing | Zoning | Floor-to-ceiling height and floor-system thickness match approved height | Always
15 | Rough-in, structure & envelope | Sheathing | Zoning | Truss slope matches approved plans (overall height) | Always
15 | Rough-in, structure & envelope | Sheathing | Roof | Roofing and roof material match drawings | Always
16 | Rough-in, structure & envelope | Framing | Structure | Seismic provisions and structure match the engineer’s drawings | Always
16 | Rough-in, structure & envelope | Framing | Air barrier | Vapour-barrier continuity provisions at interior/exterior wall intersections and top plates | Always
16 | Rough-in, structure & envelope | Framing | Air barrier | Poly boots around non-airtight boxes and non-IC pot lights | Always
16 | Rough-in, structure & envelope | Framing | Mechanical | Duct joints sealed; ductwork insulated where required, including metal joints | Always
16 | Rough-in, structure & envelope | Framing | Sprinkler | Insulation provided for sprinkler piping | Always
16 | Rough-in, structure & envelope | Framing | Zoning | Crawlspace areas comply with approved plans | Always
16 | Rough-in, structure & envelope | Framing | Stairs | Stair rise, run, tread, and headroom comply with plans and VBBL | Always
16 | Rough-in, structure & envelope | Framing | Ventilation | Mechanical ventilation matches the TECA checklist | Always
16 | Rough-in, structure & envelope | Framing | Life safety | Smoke-alarm rough-in completed | Always
16 | Rough-in, structure & envelope | Framing | Firestopping | Fire blocks, drops, and chases completed | Always
17 | Rough-in, structure & envelope | Rainscreen | Membrane | Exterior sheathing paper / membrane installed | Always
17 | Rough-in, structure & envelope | Rainscreen | Roof | Roofing and skylights installed | Always
17 | Rough-in, structure & envelope | Rainscreen | Cavity | Strapping or drainage-cavity material installed | Always
17 | Rough-in, structure & envelope | Rainscreen | Stucco | Stucco stops and flashings installed where applicable | Always
18 | Rough-in, structure & envelope | Insulation / VB | Insulation | Insulation installed to the approved assembly and R-value | Always
18 | Rough-in, structure & envelope | Insulation / VB | Vapour barrier | Vapour barrier installed and continuous | Always
18 | Rough-in, structure & envelope | Insulation / VB | Foundation | Crawl space / foundation walls below grade properly insulated | Always
18 | Rough-in, structure & envelope | Insulation / VB | Spray foam | Spray foam, if used, is specified on drawings and is a City-accepted product | If applicable
18 | Rough-in, structure & envelope | Insulation / VB | Lighting | Pot lights are IC and airtight, or a poly pan is provided | Always
18 | Rough-in, structure & envelope | Insulation / VB | Energy | Certified Energy Advisor mid-construction airtightness checklist approved | Always
18 | Rough-in, structure & envelope | Insulation / VB | Hold | No drywall or interior finishes started on exterior walls or ceilings | Always
19 | Finals | Trade finals | Plumbing | Fixtures certified; trap arms and water connections per VBBL Part 7 | Always
19 | Finals | Trade finals | Plumbing | Hot and cold supplies correct; no leaks | Always
19 | Finals | Trade finals | Plumbing | Pressure-reducing valve installed | Always
19 | Finals | Trade finals | Plumbing | Backflow prevention on hose bibs and boiler make-up water | Always
19 | Finals | Trade finals | Plumbing | Thermal expansion and T&P valve at the water heater, piped to drain | Always
19 | Finals | Trade finals | Plumbing | Water-main shut-off accessible; meter installed if on the owner’s property | Always
19 | Finals | Trade finals | Sump | Backwater valve and 90° elbow on storm-sump outlet; grouted and watertight | Always
19 | Finals | Trade finals | Sump | Drain tile and patio drains protected against backflow when required | Always
19 | Finals | Trade finals | Mechanical | Equipment does not exceed the noise by-law in operation | Always
19 | Finals | Trade finals | Mechanical | Equipment in the approved location, secured, and commissioned | Always
19 | Finals | Trade finals | Mechanical | Exterior lines protected from damage and freezing | Always
19 | Finals | Trade finals | Drain tile | Gutters and downspouts connected to underground storm piping | Always
19 | Finals | Trade finals | Gas | Notification of Completion submitted; appliances CGA / certified | If applicable
19 | Finals | Trade finals | Gas | Locations, clearances, bug screens, manuals, operation, shut-offs, vents, meter protection | If applicable
19 | Finals | Trade finals | Sprinkler | Head locations match design and site conditions | Always
19 | Finals | Trade finals | Sprinkler | Contractor on site for flow and alarm test; pump and lockable electrical switch as required | Always
19 | Finals | Trade finals | Sprinkler | Inspector’s test pipe, drain, and orifice installed; plastic water service fire-protected | Always
19 | Finals | Trade finals | Irrigation | Lawn irrigation: CSA fittings, tested backflow, pressure regulator, drained box, frost protection | If applicable
20 | Finals | Elec. final | Devices | Lighting, receptacles, switches, and cover plates complete | Always
20 | Finals | Elec. final | Devices | Equipment CSA approved or equivalent | Always
20 | Finals | Elec. final | Devices | Receptacles tested for correct polarity | Always
20 | Finals | Elec. final | Protection | GFCI where required | Always
20 | Finals | Elec. final | Protection | AFCI where required, including bedroom circuits | Always
20 | Finals | Elec. final | Devices | All single, 3-way, and 4-way switches functional | Always
20 | Finals | Elec. final | Garage | Garage ready for inspection | Always
20 | Finals | Elec. final | Low voltage | Doorbell operational | Always
20 | Finals | Elec. final | Low voltage | Security system complete; transformer and feed have approved ratings | If applicable
20 | Finals | Elec. final | Low voltage | Lighting controls installed where required | Always
20 | Finals | Elec. final | Life safety | Smoke alarms interconnected, no disconnect between overcurrent device and detectors, fully operational | Always
20 | Finals | Elec. final | Life safety | CO alarms installed (hardwired with no disconnect, or battery units fastened at specified height) | Always
20 | Finals | Elec. final | Sprinkler | Flow switch installed; disconnect locked in the on position | Always
20 | Finals | Elec. final | Panel | Panel directory completed | Always
20 | Finals | Elec. final | Panel | Cover installed flush with machine screws; overcurrent sizing correct | Always
20 | Finals | Elec. final | Panel | Boiler / furnace disconnect labelled on/off | Always
20 | Finals | Elec. final | Bonding | Gas bonding installed and accessible | Always
21 | Finals | Building final | Grade | Retaining walls and finished grades match approved plans | Always
21 | Finals | Building final | Access | Egress pathway / fire-department access path completed | Always
21 | Finals | Building final | Interior | Finished flooring completed | Always
21 | Finals | Building final | Landscape | Landscaping completed as required by the permit | If applicable
21 | Finals | Building final | Stairs | Stairs conform to by-law; sufficient headroom; exterior treads slip-resistant | Always
21 | Finals | Building final | Guards | Guards complete and non-climbable | Always
21 | Finals | Building final | Guards | Handrails complete, continuous, and graspable | Always
21 | Finals | Building final | Life safety | Smoke and carbon-monoxide alarms installed | Always
21 | Finals | Building final | Drainage | Rainwater leaders and gutters installed; groundwater contained on site | Always
21 | Finals | Building final | Envelope | Flashings and caulking installed where required | Always
21 | Finals | Building final | Seismic | Hot-water tank seismic strapping installed | Always
21 | Finals | Building final | Accessory | Detached garage completed | If applicable
21 | Finals | Building final | Trees | Replacement trees of the required size and location, if required | Always
21 | Finals | Building final | Cladding | All cladding installed; grade-to-siding clearance provided | Always
21 | Finals | Building final | Address | Address placed on the house | Always
21 | Finals | Building final | Documents | Final letters of assurance provided | Always
21 | Finals | Building final | Energy | HOT2000 energy report provided | Always
21 | Finals | Building final | Energy | Final CEA report provided | Always

## Documents
Document | Required? | Needed at stages | Received | Date | Notes
Construction Safety Plan (CSP) | Required | 1, 2
Tree protection barriers | Required | 1, 2
Hazardous materials removal documentation | Required | 2
Structural engineer letter — footings / forms | Required | 4
WorkSafeBC excavation letter | Required | 4
Geotechnical soil-bearing letter | Required | 4, 6
Non-Encroachment Certificate (NEC) | Required | 7
P.Eng. soil compaction / slab reinforcement letter | If applicable | 10
In-slab hydronic design + heat-loss summary | If applicable | 11
Energy Advisor GHG form (gas permits) | If applicable | 12
P.Eng. sealed sprinkler drawings (NFPA 13D) | Required | 12, 19
Electrical load calculation | Required | 13
P.Eng. field memo — concrete stairs / retaining walls | If applicable | 14
Pin survey — boundary walls | If applicable | 14
P.Eng. seismic / sheathing letter | Required | 15
P.Eng. deck membrane letter | If applicable | 15
Window rainscreen mock-up | Required | 15
P.Eng. framing letter | Required | 16
P.Eng. roof truss letter | Required | 16
TECA mechanical ventilation checklist | Required | 16
Certified Energy Advisor — mid-construction airtightness | Required | 18
Gas Notification of Completion | Required | 19
P.Eng. sealed sprinkler flow-verification letter | Required | 19
Schedule C-B — sprinkler field review | Required | 19
P.Eng. letter — storm sump pump | If applicable | 6, 19
Final letters of assurance (Schedules C-A / C-B) | Required | 21
HOT2000 energy report | Required | 21
Final Certified Energy Advisor report | Required | 21
City-stamped approved drawings on site | Required | 1, 4, 7, 15, 16, 21

## Permits
Permit | Required? | Detail | Number | Contractor | Status | Notes
Development / building permit | Required | Start work within 6 months of issuance or the permit becomes invalid.
Demolition permit | If applicable | Required if an existing building is coming down. Book CSP and demolition inspections first.
Sewer & water connection (SW) permit | Required | Apply before the development/building permit. Covers sanitary, storm, and water service.
Electrical — temporary construction service | Required | Temp pole or service inspected before use.
Electrical — main dwelling | Required | Rough-wire and final. Consolidate with low-voltage and garage on the same day.
Electrical — low voltage | If applicable | Doorbell, security, lighting controls. Coordinate with main electrical inspections.
Electrical — garage / detached accessory | If applicable | Coordinate with main electrical. EV charger-ready wiring is typically required.
Plumbing permit | Required | Below-slab, rough-in, and final. Coordinate with mechanical, sprinkler, drain tile, and gas.
Mechanical permit | Required | Required since 1 July 2022 before installing any heating or cooling system.
Gas permit | If applicable | Only the gas permit holder can book the final. Notification of Completion required.
Fire sprinkler permit (NFPA 13D) | Required | Inspected by a plumbing inspector. P.Eng. design and flow verification required.
Construction street-use / temporary occupancy | If applicable | Required if occupying City street, sidewalk, or boulevard for construction.

## Deficiencies
# | Stage | Inspection | Item | Description | Assigned | Opened | Closed | Status
No deficiencies recorded.

## Booking guide
BOOKING & SITE READY
BOOKING
Book online | https://plposweb.vancouver.ca/Public/Login.aspx
Create account | https://plposweb.vancouver.ca/Public/Default.aspx?PossePresentation=New&PosseObjectId=103627483
Phone (in Vancouver) | 3-1-1
Phone (outside) | 604-873-7000
Cutoff | 2:00 pm on a business day
Next-day rule | Requests received before 2 pm on a business day are typically inspected the next business day; later requests are booked two business days out.
Inspections page | https://vancouver.ca/home-property-development/inspections.aspx
Official stages PDF | https://vancouver.ca/files/cov/single-detached-house-duplex-inspection-stages-guide.pdf
New home process | https://vancouver.ca/home-property-development/build-a-new-duplex-single-detached-house-or-laneway-house.aspx
Occupancy | https://vancouver.ca/home-property-development/occupancy-permit.aspx
READY FOR THE INSPECTOR
☐ | Site is safe, accessible, and reasonably tidy
☐ | City-stamped drawings and the permit are on site
☐ | A site representative can meet the inspector if required
☐ | Previous deficiencies on this stage are fully corrected
☐ | Work for this stage is complete and not yet covered
REINSPECTION FEE TRIGGERS
• | Site inaccessible or unsafe; required safety measures missing
• | Plans or a site representative not available when required
• | Incomplete work, or work progressed past the inspection point (needs uncovering)
• | Previous deficiencies not fully corrected
• | Work not ready at the scheduled time
• | Cancelled after the 2 pm deadline
• | Uncoordinated trade-inspection requests
ON-SITE DOCUMENTS (EVERY VISIT)
• | One printed copy of the City-approved permit.
• | One full-size set of City-approved drawings with the acceptance stamp.
• | Stage-specific letters (P.Eng., CEA, NEC, WorkSafeBC, etc.) listed on the Documents sheet.
• | A site representative who can meet the inspector if asked.